## Plannig
Epic | UserStory | Task | Responsible | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12
Visualize parts counter | Build microservice to read PLC data & publish to UNS | Credentials to connect to OPCUA server | bar: 2026-06-03
List of required TAG names | bar: 2026-06-03
Verify connection to OPCUA server | bar: 2026-06-03
Credentials to connect to Broker | bar: 2026-06-03
Verify connection to broker | bar: 2026-06-03
Define UNS topic | bar: 2026-06-03
Define payload structure | bar: 2026-06-03
Verify data pulling method | bar: 2026-06-03 to 2026-06-04
build part counter logic | bar: 2026-06-03 to 2026-06-04
Create defined payload & publish to broker | bar: 2026-06-05
| Build microservice to store data to Postgres | Credentials to connect to Broker | bar: 2026-06-04
Verify connection to broker | bar: 2026-06-04
Subscribe to relavant topic | bar: 2026-06-05
Define database schema | bar: 2026-06-08
Verify connection to Postgres | bar: 2026-06-08
Ingest data to Postgres | bar: 2026-06-09
| Build Grafana dashboard | Verify Grafana Docker image | bar: 2026-06-04
Install MQTT & Postgres plugin | bar: 2026-06-04
Configure connection to MQTT & Postgres | bar: 2026-06-05 to 2026-06-08
Agree on what & how to visualize | bar: 2026-06-05 to 2026-06-08
Build the dashboard | bar: 2026-06-08 to 2026-06-09
Release the dashboard the end user | bar: 2026-06-10
User buyoff | bar: 2026-06-10
| Build REST API to interface database | Verify connection to Postgres | bar: 2026-06-08
Define API end point | bar: 2026-06-08
Implement handlers for each end point | bar: 2026-06-09
Create query logic | bar: 2026-06-09
Planning & presentations | Planning | Daily Standup call 15 min
| Prepare peresentations | Final presenation | bar: 2026-06-11 to 2026-06-12

## Testing plans
Test plan | If it happens, what to do?
Device can't communiate like PLC to micro service and microservice to MQTT | Display an error on the dashboard so end user can verify
A TAG is missing | Display an error (Missing TAG) on top of the screen
OPC server is down/failed to connect to server | Display an error on the dashboard so end user can verify
Can't communicate to DB | Display an error on the dashboard so end user can verify
Data type mismatch | Display errow with specific info